## Tech Scoring Matrix
KisanPay — Technology Scoring Matrix ¦ MGT 589 Payment Technology ¦ Phase 2: Part B
Scoring Scale: 1=Very Poor 2=Poor 3=Average 4=Good 5=Excellent ¦ Weights sum to 100%
Payment Technology | Cost (30%) | Speed (25%) | Security (20%) | Scalability (15%) | UX (10%) | Weighted Score | Rank | KisanPay Status | Recommendation
CRITERIA WEIGHTS → | 30% | 25% | 20% | 15% | 10% | 100%
RAAST P2P / P2M (SBP Real-Time Rail) | 5 | 5 | 5 | 5 | 4 | 4.9 | 1 | Core Platform Rail | ADOPT — Primary
NADRA eKYC API (Biometric Identity) | 3 | 5 | 5 | 5 | 5 | 4.4 | 2 | MoU Required | ADOPT — Priority 1
USSD / IVR Interface (*123#) | 5 | 4 | 3 | 5 | 5 | 4.35 | 3 | Planned — Q3 2026 | ADOPT — Priority 2
Flutter Cross-Platform Mobile App (Arthi) | 4 | 5 | 4 | 4 | 4 | 4.25 | 4 | MVP Development | ADOPT — Q3 2026
RAAST P2M QR Code (Interoperable) | 5 | 4 | 4 | 3 | 2 | 3.95 | 5 | Year 2 Planned | ADOPT — Year 2
AI Alternative Credit Scoring Engine (ML) | 3 | 5 | 4 | 4 | 3 | 3.85 | 6 | Prototype Phase | BUILD — Year 1
Open Banking APIs (SBP Open Finance) | 3 | 4 | 4 | 4 | 3 | 3.6 | 7 | Regulatory Pending | BUILD — Year 2
Agent Cash Network (JazzCash/Easypaisa API) | 3 | 2 | 3 | 5 | 4 | 3.15 | 8 | Active via Partners | INTEGRATE
Embedded BNPL / Working Capital Advance | 2 | 4 | 3 | 3 | 4 | 3.05 | 9 | Product-Ready (PSP pending) | LAUNCH post-PSP
★ Green shading = Top-2 Scoring Technologies ¦ Red shading = Bottom-2 Performers ¦ Weighted Score = Cost 30% ¦ Speed 25% ¦ Security 20% ¦ Scalability 15% ¦ UX 10%

## Compliance Map
KisanPay — Regulatory Compliance Map ¦ MGT 589 Payment Technology ¦ Phase 3: Part A
Status: ✓ Compliant ¦ ◑ Partial ¦ ✗ Gap ¦ N/A ¦ Risk: HIGH / Medium / Low
Regulatory Dimension | Regulation / Law | Specific Obligation for KisanPay | Current Status | Compliance | Risk Level | Risk
AML / KYC | Tiered KYC — Basic | SBP AML/CFT Regs 2023 | CNIC-only KYC for transactions < PKR 50,000/year; no additional docs required | CNIC collection defined; agent-verified | ◑ Partial | Medium
| Tiered KYC — Full | SBP AML/CFT Regs 2023 | Full KYC (income proof, address, purpose) for transactions ≥ PKR 50,000/year | Process designed; not yet deployed | ◑ Partial | Medium
| Transaction Monitoring | AML Act 2010; SBP Circular | AI-based monitoring for transactions > PKR 200,000; flag anomalies; monthly SBP reporting | In development — not operational | ✗ Gap | HIGH
| SAR Filing | AML Act 2010, Section 7 | File SARs with FMU within 7 days of detection of suspicious transaction | FMU API not integrated; mechanism absent | ✗ Gap | HIGH
| Customer Due Diligence (CDD) | FATF Rec. 10; SBP CDD Regs | Standard CDD for all customers; verify identity before first transaction; ongoing monitoring | Partially implemented via CNIC verification | ◑ Partial | Medium
| Enhanced Due Diligence (EDD) — Arthis | FATF Rec. 12; SBP CDD Regs | EDD required for arthis as high-value cash handlers: source of funds, site visit, periodic review | No EDD programme defined | ✗ Gap | HIGH
| 10-Year Record Retention | AML Act 2010, Section 6 | All transaction records retained for minimum 10 years; immutable audit trail required | Planned on AWS Mumbai (SBP-approved region) | ◑ Partial | Low
LICENSING | SBP PSP Licence | SBP Payment Systems Regulations 2019 | PSP licence required before processing any commercial payment transactions | Application not yet filed — CRITICAL pre-launch requirement | ✗ Gap | HIGH
| SBP EMI Licence | SBP EMI Regulations 2023 | E-Money Institution licence; PKR 200M minimum paid-up capital | Year 2 target; operating as EMI-agent in Year 1 | N/A Year 1 | Medium
| RAAST Sponsoring Bank MoU | SBP RAAST Participation Agreement | Commercial bank sponsorship for RAAST sub-member access; ISO 20022 compliance | Under negotiation with Meezan Bank | ◑ Partial | Medium
| NADRA eKYC MoU | NADRA Act 2000; SBP Digital KYC Framework | Formal MoU with NADRA required before Verisys biometric API access | Engagement not initiated | ✗ Gap | Medium
| SECP Company Registration | Companies Act 2017 | Private Limited Company registration under Companies Act 2017 | Completed at incorporation | ✓ Compliant | Nil
DATA PROTECTION | PDPA 2023 Compliance | Personal Data Protection Act 2023 | Legal basis for all data processing; privacy notices; DPO appointment required | Privacy policy draft incomplete; no DPO appointed | ✗ Gap | Medium
| SBP Data Localization | SBP Data Localization Policy | All payment transaction data stored on SBP-approved servers within Pakistan | Compliant — AWS Mumbai is SBP-approved region | ✓ Compliant | Nil
| PCI-DSS | PCI Security Standards Council | Required if card data is processed; KisanPay Phase 1 does not process card data | Not applicable in Phase 1 | N/A | Nil
CRYPTO / VASP | Cryptocurrency Prohibition | SBP Circular No. 3 (2021) | KisanPay does not handle cryptocurrency; SBP 2021 Circular prohibits crypto for payments | KisanPay is crypto-free by design | ✓ Compliant | Nil
| SECP VASP Registration | SECP VASP Consultation Paper 2024 | Required only if dealing in virtual assets — KisanPay does not | Not applicable | N/A | Nil
CROSS-BORDER | SBP FX Regulations | SBP Foreign Exchange Regulations | Phase 1 is entirely domestic — no cross-border transactions; FX regulations not applicable | Domestic-only operations confirmed | N/A | Nil
| SWIFT / Correspondent Banking | SBP SWIFT Compliance | Phase 1 domestic only; no SWIFT transactions required | Not applicable — domestic RAAST only | N/A | Nil

## Gap Analysis
KisanPay — Compliance Gap Analysis & Prioritised Remediation Plan ¦ Phase 3: Part B
Sorted: HIGH → Medium → Low ¦ All gaps must be closed before commercial launch
Compliance Gap | Detailed Description | Risk Level | Remediation Action Required | Timeline | Est. Cost (PKR) | Responsible Function
SBP PSP Licence (Not Filed) | PSP licence required before first commercial transaction; gates RAAST, USSD, and Working Capital Advance product simultaneously | HIGH | File SBP PSP application Month 1; engage external regulatory counsel; prepare business plan, capital adequacy proof, and compliance framework | Month 1–6 | PKR 2,000,000–3,000,000 | CEO + External Legal Counsel
SAR Filing Infrastructure (Absent) | No SAR filing mechanism exists; FMU API not integrated; must be operational before any commercial transaction to comply with AML Act 2010 Section 7 | HIGH | Hire AML Compliance Officer Month 1; integrate FMU API; establish monthly STR reporting to SBP; staff training on red-flag indicators | Month 1–2 (8 weeks) | PKR 1,500,000 | Legal + IT + Compliance Officer
Automated Transaction Monitoring (Not Built) | No automated system to flag suspicious transactions; manual review insufficient at scale; required for AML Act compliance and SBP inspection readiness | HIGH | Deploy rule-based monitoring Month 2 (flag txns >PKR 200K); upgrade to ML-based anomaly detection Month 4; quarterly tuning review | Month 2–4 | PKR 2,500,000 | CTO + Compliance Officer
Arthi Enhanced Due Diligence (Undefined) | No EDD programme for arthis as high-volume cash handlers; FATF Rec 12 requires enhanced monitoring; each arthi may handle PKR 50–500K/day | HIGH | Design arthi risk-rating model (transaction volume tiers); mandatory source-of-funds docs; biennial site verification; escalation process for red-flag transactions | Month 1–3 (12 weeks) | PKR 500,000 | Operations + Compliance
PDPA 2023 — No DPO & Incomplete Privacy Docs | DPO not appointed; privacy notices absent; data processing activities not documented; consent mechanisms not implemented for IVR voice data | Medium | Appoint DPO (internal or outsourced) by Month 2; draft privacy policy; document all processing activities in ROPA; implement consent capture for IVR | Month 2 (4–6 weeks) | PKR 600,000 | Legal + IT
NADRA eKYC MoU (Not Initiated) | eKYC API integration requires formal MoU with NADRA; engagement with Ministry of Interior not started; blocks scalable digital onboarding | Medium | Initiate formal NADRA engagement via Ministry of Interior Month 1; prepare legal MoU draft; engage NADRA commercial division; budget for scanners | Month 1–6 (4–6 months) | PKR 500,000 legal + PKR 7,500,000 hardware | Management + Legal + IT
RAAST Sponsoring Bank MoU (Under Negotiation) | RAAST sub-member access requires executed commercial bank MoU; without this KisanPay cannot route any RAAST transactions; pilot launch dependency | Medium | Finalize commercial terms with Meezan Bank; legal review of MoU; negotiate SLA for RAAST API uptime; sign by Month 3 | Month 1–3 (8–12 weeks) | PKR 300,000 | Business Development + Legal
Tiered KYC — Full Tier Not Deployed | Full KYC process designed but not yet deployable; blocks serving farmers with annual transactions ≥ PKR 50,000 | Medium | Complete digital KYC workflow in Flutter app and USSD; integrate CNIC verification; design income-proof document upload; test with 50 pilot users before launch | Month 2–3 (6 weeks) | PKR 400,000 | IT + Operations
10-Year Record Retention (Partial) | AWS deployment planned but immutable ledger architecture not finalized; SBP inspection readiness requires tested backup and recovery | Low | Finalize immutable PostgreSQL ledger with SHA-256 row hashing; implement AWS S3 Glacier for archival; document and test backup/recovery quarterly | Month 3 (4 weeks) | PKR 200,000/year (AWS storage) | CTO + IT
TOTAL GAPS: 9 ¦ HIGH: 4 ¦ Medium: 4 ¦ Low: 1

## Implementation Gantt
KisanPay — 12-Month Implementation Roadmap (Gantt Chart) ¦ MGT 589 ¦ Final Phase
● = Active Phase ¦ Blue=Compliance ¦ Green=Technology ¦ Orange=Commercial ¦ Purple=Product
|  | Q1 — Pilot Preparation |  |  | Q2 — Pilot Launch |  |  | Q3 — Punjab Commercial Launch |  |  | Q4 — Sindh Expansion + AI Upgrade
Initiative / Milestone | Category | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | Owner | Priority
SBP PSP Licence Filing & Approval | COMPLIANCE | ● | ● | ● | ● | ● | ● | [6 empty] | CEO + Legal | CRITICAL
RAAST Sponsoring Bank MoU | COMPLIANCE | ● | ● | ● | [9 empty] | Business Dev | CRITICAL
SAR Filing + FMU API Integration | COMPLIANCE | ● | ● | [10 empty] | Legal + IT | CRITICAL
Arthi EDD Programme | COMPLIANCE | ● | ● | ● | [9 empty] | Ops + Compliance | CRITICAL
PDPA Compliance + DPO Appointment | COMPLIANCE |  | ● | [10 empty] | Legal | HIGH
Transaction Monitoring (Rule→ML) | COMPLIANCE |  | ● | ● | ● | [8 empty] | CTO + Compliance | CRITICAL
NADRA eKYC MoU Engagement | COMPLIANCE | ● | ● | ● | ● | ● | ● | [6 empty] | Management + Legal | HIGH
USSD / IVR Platform Development | TECH | ● | ● | ● | ● | [8 empty] | CTO | CRITICAL
Flutter Arthi App MVP | TECH | ● | ● | ● | ● | ● | [7 empty] | CTO + Dev Team | CRITICAL
NADRA eKYC API Integration (Post-MoU) | TECH | [5 empty] | ● | ● | ● |  |  |  |  | IT | HIGH
AI Credit Scoring Engine v1.0 | TECH | [8 empty] | ● | ● | ● | ● | Data Science | HIGH
Open Banking API Technical Build | TECH |  |  |  | ● | ● | ● | ● | ● | ● | ● | ● | ● | CTO | MEDIUM
Pilot Launch — 500 Arthis (Multan) | COMMERCIAL |  |  |  | ● | ● | ● | [6 empty] | COO | CRITICAL
Commercial Launch — Punjab Province | COMMERCIAL | [6 empty] | ● | ● | ● |  |  |  | COO + Sales | HIGH
Sindh Expansion (Larkana+Hyderabad) | COMMERCIAL | [9 empty] | ● | ● | ● | COO + Sales | HIGH
Working Capital Advance Product Launch | PRODUCT | [5 empty] | ● | ● | [5 empty] | Product + Legal | HIGH
RAAST P2M QR — Input Supplier Rollout | PRODUCT | [9 empty] | ● | ● | ● | Product + BD | MEDIUM
Investor Reporting + KPI Dashboard | PRODUCT |  |  | ● |  |  | ● |  |  | ● |  |  | ● | CEO + Finance | MEDIUM

## KPI Dashboard
KisanPay — KPI Dashboard & Success Metrics ¦ MGT 589 ¦ Final Phase: Section 4.5
Source: PDF Report Table 4.5 ¦ All figures verified against Financial Projections sheet
Key Performance Indicator (KPI) | Baseline (Current) | Year 1 Target (2027) | Year 3 Target (2029) | Measurement Method | Review Frequency
Farmers with digital payment history | 0 farmers | 50,000 farmers | 200,000 farmers | KisanPay platform database count | Monthly
Total transaction volume processed | PKR 0 | PKR 2.5 billion | PKR 10 billion+ | RAAST API + platform ledger | Monthly
Average payment settlement time | 30–45 days (cheque) | < 2 minutes (RAAST) | Real-time: 100% | Transaction log timestamps | Weekly
Farmer formal credit access rate | 12% (SBP baseline) | 18% | 35% | SBP credit bureau + partner bank referrals | Quarterly
Arthi operational cost reduction | 0% (baseline) | 10% reduction | 25% reduction | Arthi survey + cash logistics audit | Semi-annual
Working capital advance NPL rate | N/A | < 5% | < 3% | Platform credit book monitoring | Monthly
RAAST transaction success rate | N/A | > 99.5% | > 99.9% | RAAST API response monitoring | Daily
Arthi Net Promoter Score (NPS) | N/A (no product) | ≥ 7 / 10 | ≥ 8.5 / 10 | Quarterly arthi survey (50-sample) | Quarterly
Regulatory compliance score | N/A | 100% pre-launch gaps closed | Zero enforcement actions | Internal compliance audit + SBP inspection | Monthly
Farmer informal credit cost saved | PKR 0 | PKR 225M (9,000 farmers × PKR 25K) | PKR 1.125B | WC advance APR vs. informal rate delta | Annual

## Payment Flow Diagram
KisanPay — Payment Flow Diagram ¦ RAAST Variant A (Banked Farmer Crop Sale) ¦ Phase 1: Section 1.8
Source: PDF Report Figure 1.1 ¦ Colour codes: Blue=Authorization ¦ Orange=Clearing ¦ Green=Settlement
ARTHI (Payer) | KISANPAY (Orchestration) | ISSUING BANK (Meezan Bank) | RAAST SWITCH (SBP) | ACQUIRING BANK (UBL/MCB) | FARMER (Payee) | Stage
Step 1: Initiates payment (CNIC + amount) | → Receives payment request |  |  |  |  | AUTHORIZATION Steps 1–4
Step 2: Validates request (CNIC, limits, AML)
| Step 3: Sends ISO 20022 auth request → | Step 3: Receives auth request | → Forwards to RAAST
|  |  | Step 4: Auth confirmed; transaction locked | ← Confirmed | ← Notified
|  |  | Step 5: Forwards ISO 20022 txn data → | Step 5: Receives txn data |  | CLEARING Steps 5–8
|  |  |  | Step 6: Validates farmer account | ← Account validated
| Step 7 & 8: KisanPay ledger SHA-256 hash recorded |  | Step 7: Interbank obligation computed at SBP
|  | Step 9: SBP debits Meezan Bank | Step 9: SBP executes funds transfer | Step 9: SBP credits UBL/MCB |  | SETTLEMENT Steps 9–12
|  |  |  | Step 10: Farmer account credited | Step 10: PKR 120,000 credited; SMS sent (Urdu)
| Step 11 & 12: Credit score updated; arthi dashboard refreshed | ← pacs.002 confirm sent | Step 11: Settlement confirm (pacs.002) sent
Total elapsed time: < 30 seconds from initiation to farmer credit ¦ Blue = Authorization (Steps 1–4) ¦ Orange = Clearing (Steps 5–8) ¦ Green = Settlement (Steps 9–12)

## Financial Projections
KisanPay — Revenue & Impact Projections (3-Year) ¦ Final Phase: Strategy
Revenue Model: 0.5% fee on Working Capital Advances + PKR 500/month Arthi Subscription (Year 2+) ¦ All figures in PKR
Metric | Assumptions | Year 1 (2027) | Year 2 (2028) | Year 3 (2029) | CAGR | Notes
── ASSUMPTIONS ──
Fee Rate | Platform fee on advances | 0.5% | 0.5% | 0.5% |  | Source: PDF Report Section 1.1
Sub Fee | Arthi monthly subscription | PKR 0 (free) | PKR 500/mo | PKR 500/mo |  | Free Year 1; paid from Year 2
Adv % | Working Capital / Total Vol | 40% | 40% | 40% |  | 70% disbursed upfront
Avg Txn | Average transaction value | PKR 80,000 | PKR 80,000 | PKR 80,000 |  | Blended average across all types
VOLUME METRICS
Registered Arthis | Annual net adds | 5000 | 20000 | 45000 | 200% | Target: 45K total arthis in Pakistan
Active Farmers (Digital) | % of arthis × 10 | 50000 | 150000 | 200000 | 100% | 10 farmers per arthi avg
Total Transaction Volume (PKR) | Avg PKR 80K/txn | 2500000000 | 6000000000 | 10000000000 | 100% | PKR 2.5B / 6B / 10B
Working Capital Advances (PKR) | 40% of transaction volume | 1000000000 | 2400000000 | 4000000000 | 100% | 70% disbursed upfront to farmer
REVENUE
Platform Fee (0.5% on advances) (PKR) | 0.5% × Working Capital Advances | 5000000 | 12000000 | 20000000 | 100% | Primary Year 1 revenue stream
Arthi Subscription (PKR 500/month) (PKR) | PKR 500/mo × registered arthis | 0% | 120000000 | 270000000 | n/a | Year 2+ only; Year 1 = PKR 0 (free introductory period)
Total Revenue (PKR) | Platform Fee + Arthi Subscription | 500000000% | 132000000 | 290000000 | 661.6% | Year 1 = fee only (PKR 5M); subscription free
IMPACT METRICS
Farmer Interest Savings (PKR) | 60%→18% APR delta on WC advances | 420000000 | 1008000000 | 1680000000 | 100% | PKR saved vs. informal 60% APR borrowing
Arthi Cash Logistics Saved (PKR) | PKR 50K/month per arthi eliminated | 3000000000 | 12000000000 | 27000000000 | 200% | Cash logistics cost eliminated by digital payments
Formal Credit Access Rate | % farmers with digital payment history | 12% | 22% | 35% | N/A | SBP FY2025 baseline: 12%